## Module Status
NEX ERP - Module Delivery Status
Status as at 1 September 2026. Assessed from the codebase: route map, backend endpoint counts, and placeholder screens.
Yellow cells are for you to fill in. '% Complete' and 'Effort' are estimates - adjust to match your own planning.
Module | Area | Status | Est. % Complete | What Is Delivered | Remaining Gaps / Work | Backend Endpoints | Est. Effort (dev-days) | Priority | Owner | Target Start | Target Finish
Dashboard | Core | Done | 100% | KPI cards, leads pipeline chart, quotations by status, attendance summary, recent orders, daily time tracker | No date-range filter or export on analytics | 1 | 0 | Low
Employees / People Hub | HRMS | Done | 100% | Directory, 360 profiles, org chart, document vault, onboarding list, profile tabs | None outstanding | 23 | 0 | Low
Recruitment & ATS | HRMS | Done | 100% | Job postings, candidate pipeline, interviews, reports, public careers portal, offer letters (DOCX + HTML templates) | None outstanding | 22 | 0 | Low
Attendance & Leave | HRMS | Done | 100% | Clock in/out with geofence, all-attendance grid, leave requests & approvals, shift roster visibility, overtime tracking | None outstanding | 26 | 0 | Low
Performance & Reviews | HRMS | Done | 100% | Review cycles, KPI goals, ratings, appraisal records | None outstanding | 24 | 0 | Low
Projects & Issue Tracking | Delivery | Done | 100% | Project boards, issues, sprints, milestones, project onboarding, sequential issue IDs, client association | None outstanding | 56 | 0 | Low
CRM - Leads & Pipeline | Revenue | Done | 100% | Kanban leads board, lead dashboard, follow-ups, lead contacts, quotation conversion | None outstanding | 16 | 0 | Low
Sales (Quotations & Orders) | Revenue | Done | 95% | Quotation builder with PDF export, sales orders, follow-ups | Point of Sale screen is thin - only 6 endpoints across the whole module | 6 | 5 | Medium
Settings & Administration | Platform | Done | 100% | Master data, company profile, role permission matrix, system settings, payroll rules | None outstanding | 4 | 0 | Low
Helpdesk / Tickets | Platform | Done | 100% | Ticket CRUD, threaded comments, activity log, multi-image upload to ImageKit, Quill rich-text editor, role-scoped visibility, auto-assign to dev PM, same-department reassignment, reporter close-off, header alert badge | Email / push notification on new ticket not yet wired. Default ticket assignee must be set in System Settings. | 11 | 3 | Medium
Payroll & Expenses | Finance | Partial | 60% | Backend complete: salary structures, payslip generation, LOP attendance sync, PF/ESI/TDS engine, expense claims | Web UI is a single placeholder screen. Payslip viewer, bulk payslip emailer and expense approval flow not built. | 21 | 25 | High
Assets & IT Inventory | Operations | Partial | 55% | Backend complete: inventory, assignments, hardware requests, maintenance logs. Mobile Assets screens exist. | Web UI placeholder. Inventory grid, custody tracking, warranty and depreciation views pending. | 26 | 20 | High
Clients | Revenue | Partial | 50% | Client list and profile scaffolding, project/billing association | Placeholder content in both list and profile. Billing and invoice linkage incomplete. | 10 | 12 | Medium
Offboarding | HRMS | Partial | 45% | Exit initiation and exit interview backend | UI placeholder. Clearance checklist, full & final settlement and asset-return handoff pending. | 7 | 12 | Medium
Appreciation & Culture | HRMS | Partial | 40% | Kudos feed and awards backend | UI placeholder. Badges, award types (Star/Trophy/Ribbon) and leaderboard pending. | 7 | 8 | Low
Timesheets | Delivery | Partial | 50% | Timesheet entry screen present | No dedicated backend module - relies on Projects. Approval workflow and workload balancing pending. | 0 | 8 | Medium
Employee Onboarding | HRMS | Partial | 70% | Digital onboarding flow and employee self-service steps | Document collection and e-signature steps incomplete. | 8 | 6 | Medium
Kiosk (Biometric Punch) | Attendance | Partial | 60% | Kiosk punch screen with company-scoped route | Selfie capture and device pairing hardening pending. | 2 | 5 | Medium
Mobile App (Android) | Mobile | Partial | 65% | Auth, Dashboard, ESS, Payslips, CRM, Projects, Field Visits, Assets, Notifications, Onboarding screens | Release signing config, offline sync, biometric lock and push notifications outstanding. | 0 | 20 | High
Public Site & Careers Portal | Marketing | Done | 100% | Landing page, public careers portal, APK download endpoint | None outstanding | 0 | 0 | Low
TOTAL / AVERAGE
Note on D27: Simple average of the per-module estimates, not weighted by module size.

## Summary
Delivery Summary
Status | Modules | Effort Remaining (dev-days)
Done
Partial
Not Started
TOTAL
Overall completion (avg)
Team size (developers) | 2.5
Est. calendar weeks remaining
Assumption: '% Complete' and 'Effort' are my estimates from reading the codebase, not measured velocity.
Source: NEX ERP repository, branch 'main', assessed 1 September 2026.
Note on B10: Blue = your input. Change this to re-forecast the weeks below. You told me 2-3 developers, so 2.5 is used as the midpoint.
Note on B11: Remaining dev-days / developers / 5 working days. Assumes fully parallel work with no dependencies, holidays or BAU support - treat it as a floor, not a plan.

## How To Use
How to use this tracker
Cells you fill in | Every yellow cell: Owner, Target Start, Target Finish (Module Status tab) and Team size (Summary tab).
Cells you should not overwrite | The TOTAL row and everything on Summary - they are live formulas that recalculate.
Status | Pick from the dropdown: Done / Partial / Not Started. Summary counts update automatically.
Est. % Complete | My estimate of how much of the module is built. Overwrite freely.
Backend Endpoints | Actual count of @Get/@Post/@Patch/@Put/@Delete handlers in that backend module. Measured, not estimated.
Est. Effort (dev-days) | My estimate of the work left. One dev-day = one developer for one working day.
Date format | Type dates as DD-MMM-YYYY, for example 15-Oct-2026.
Example row | Payroll & Expenses ¦ Partial ¦ 60% ¦ 25 dev-days ¦ High ¦ Owner: Mohit S. ¦ Start: 15-Sep-2026 ¦ Finish: 24-Oct-2026
How status was determined
1. Frontend route map read from app.routes.ts (50 routes).
2. Backend endpoint decorators counted per module directory.
3. Modules whose screens still contain 'Coming Soon' / TODO placeholders were marked Partial:
assets, appreciation, clients (list + profile), offboarding, payroll.
4. The Done/WIP badges the app itself renders in the sidebar were used as a cross-check.