## Tasks
S.No | Added Date | Task | Category | Status | Start Date | End Date | Remarks | Testing By | Final Testing
1 | 2026-09-30 | Replace nex.ces-pl.com with mira.ces-pl.com everywhere (app links, emails, offer letter links, config) | Global / Dashboard | Pending |  |  |  |  | Pending
2 | 2026-09-30 | Dashboard order: My Tasks → Projects → My Tickets → Employee Appreciation | Global / Dashboard | Pending |  |  |  |  | Pending
3 | 2026-09-30 | Move Calendar to just below the KPI section | Global / Dashboard | Pending |  |  |  |  | Pending
4 | 2026-09-30 | Notice board date filter: last 30 days, last 70 days, custom date range | Global / Dashboard | Pending |  |  | ?? Confirm: 70 or 90 days? |  | Pending
5 | 2026-09-30 | Clicking outside an open dropdown closes it, on every form | Global / Dashboard | Pending |  |  |  |  | Pending
6 | 2026-09-30 | Recruiter is a required field | Job Creation | Pending |  |  |  |  | Pending
7 | 2026-09-30 | Remove 'Unassigned' from the recruiter list | Job Creation | Pending |  |  |  |  | Pending
8 | 2026-09-30 | Auto-generated unique Job ID in the employee ID style (e.g. JOB-0001) | Job Creation | Pending |  |  | ?? Confirm: ID format |  | Pending
9 | 2026-09-30 | AI description uses the details already filled in (title, department, experience, skills, salary) | Job Creation | Pending |  |  |  |  | Pending
10 | 2026-09-30 | HR can add interview rounds while creating a job (HR / Manager / Technical / custom) and set their order | Job Creation | Pending |  |  |  |  | Pending
11 | 2026-09-30 | Interview tab shows the rounds in that same order | Job Creation | Pending |  |  |  |  | Pending
12 | 2026-09-30 | Duplicate option copies an existing job into a new draft | Job Creation | Pending |  |  |  |  | Pending
13 | 2026-09-30 | Reopening a closed job clears the end date and makes it required again | Job Creation | Pending |  |  |  |  | Pending
14 | 2026-09-30 | Listing shows number of openings per job | Job Listing & Detail | Pending |  |  |  |  | Pending
15 | 2026-09-30 | Listing shows total applicants and a count per stage | Job Listing & Detail | Pending |  |  |  |  | Pending
16 | 2026-09-30 | Job expires automatically once all openings are filled (e.g. 5 of 5) | Job Listing & Detail | Pending |  |  | ?? Confirm: count hired or applied? |  | Pending
17 | 2026-09-30 | Job detail KPIs: Hired, Active Pipeline, Rejected, On Hold | Job Listing & Detail | Pending |  |  |  |  | Pending
18 | 2026-09-30 | Export option downloads the job list (Excel/CSV) | Job Listing & Detail | Pending |  |  |  |  | Pending
19 | 2026-09-30 | Move the chat widget (Tawk) on the job listing page from right to left | Job Listing & Detail | Pending |  |  |  |  | Pending
20 | 2026-09-30 | Candidates must be 18+ (checked from date of birth) | Job Application | Pending |  |  |  |  | Pending
21 | 2026-09-30 | Photograph is mandatory | Job Application | Pending |  |  |  |  | Pending
22 | 2026-09-30 | Resume is mandatory | Job Application | Pending |  |  |  |  | Pending
23 | 2026-09-30 | After applying, email the candidate and HR | Job Application | Pending |  |  |  |  | Pending
24 | 2026-09-30 | Rejecting a candidate requires a reason | Candidate / ATS | Pending |  |  |  |  | Pending
25 | 2026-09-30 | Putting a candidate On Hold requires a reason | Candidate / ATS | Pending |  |  |  |  | Pending
26 | 2026-09-30 | On a stage change, ask 'Notify candidate?' and send the email only on Yes | Candidate / ATS | Pending |  |  |  |  | Pending
27 | 2026-09-30 | Follow-up tab on each candidate (notes and dates) | Candidate / ATS | Pending |  |  |  |  | Pending
28 | 2026-09-30 | Follow-up filter for due or pending follow-ups | Candidate / ATS | Pending |  |  |  |  | Pending
29 | 2026-09-30 | Admin report per HR over a date range: jobs posted, hired, rejected, full details | Candidate / ATS | Pending |  |  |  |  | Pending
30 | 2026-09-30 | Offer letter events (sent, viewed, accepted, expired) show in the candidate history | Candidate / ATS | Pending |  |  |  |  | Pending
31 | 2026-09-30 | Scheduling shows the designation the candidate applied for | Interviews | Pending |  |  |  |  | Pending
32 | 2026-09-30 | Interviewer email includes candidate name, date and time, and meeting link | Interviews | Pending |  |  |  |  | Pending
33 | 2026-09-30 | Interviewer email includes a link to the candidate's profile in the portal | Interviews | Pending |  |  |  |  | Pending
34 | 2026-09-30 | Separate 'Add Interview' button: choose a job and a candidate who isn't hired yet | Interviews | Pending |  |  |  |  | Pending
35 | 2026-09-30 | Interview mode options: On-premises, Phone, Video, Other | Interviews | Pending |  |  |  |  | Pending
36 | 2026-09-30 | Annexure templates by employee type (Contractual, Engineer, Trainee and so on), picked automatically | Offer Letter & Annexure | Pending |  |  |  |  | Pending
37 | 2026-09-30 | TDS templates by employee type | Offer Letter & Annexure | Pending |  |  |  |  | Pending
38 | 2026-09-30 | Variable salary in the annexure comes from the job and its salary components | Offer Letter & Annexure | Pending |  |  |  |  | Pending
39 | 2026-09-30 | Salary groups and deductions, set up once and reused | Offer Letter & Annexure | Pending |  |  |  |  | Pending
40 | 2026-09-30 | TDS calculated on the months left in the financial year | Offer Letter & Annexure | Pending |  |  |  |  | Pending
41 | 2026-09-30 | Send the annexure automatically when a candidate moves to Offered | Offer Letter & Annexure | Pending |  |  |  |  | Pending
42 | 2026-09-30 | BUG: annexure doesn't show on the offer letter | Offer Letter & Annexure | Pending |  |  | Bug |  | Pending
43 | 2026-09-30 | Offer letter expires 1 week after sending by default (HR can change this) | Offer Letter & Annexure | Pending |  |  |  |  | Pending
44 | 2026-09-30 | Show the expiry date in the tool and on the offer letter link | Offer Letter & Annexure | Pending |  |  |  |  | Pending
45 | 2026-09-30 | Annexure acknowledgement with a due date | Offer Letter & Annexure | Pending |  |  |  |  | Pending
46 | 2026-09-30 | 'Expired' status in the offer letter filters | Offer Letter & Annexure | Pending |  |  |  |  | Pending
47 | 2026-09-30 | Remove the orange line at the top of the offer letter | Offer Letter & Annexure | Pending |  |  |  |  | Pending
48 | 2026-09-30 | New 'Offer Letters' section (like Documents) listing every offer letter | Offer Letter & Annexure | Pending |  |  |  |  | Pending
49 | 2026-09-30 | Offer Letters filters: job, department, date (day, week, multiple months, custom) | Offer Letter & Annexure | Pending |  |  |  |  | Pending
50 | 2026-09-30 | Generate an employee code automatically and email it | Onboarding → Employee | Pending |  |  |  |  | Pending
51 | 2026-09-30 | Before Onboarded → Completed, HR chooses what to collect (documents, bank details, directory fields) | Onboarding → Employee | Pending |  |  |  |  | Pending
52 | 2026-09-30 | Attach the resume to the employee profile automatically | Onboarding → Employee | Pending |  |  |  |  | Pending
53 | 2026-09-30 | Past experience with a reference contact for each employer, for verification | Onboarding → Employee | Pending |  |  |  |  | Pending
54 | 2026-09-30 | After HR approves, send a confirmation email with the employee ID | Onboarding → Employee | Pending |  |  |  |  | Pending
55 | 2026-09-30 | Offboarding section under Employees | Onboarding → Employee | Pending |  |  | ?? Confirm: what steps does offboarding need? |  | Pending
56 | 2026-09-30 | Rename 'Request' to 'Approval Request' | Delivery | Pending |  |  |  |  | Pending
57 | 2026-09-30 | Add a Sign-off tab | Delivery | Pending |  |  |  |  | Pending
58 | 2026-09-30 | Add a Project Onboarding tab at the top of Delivery | Delivery | Pending |  |  |  |  | Pending
59 | 2026-09-30 | Take 'My Field Visits' out of the menu and show it only inside the Field Visits tab | Delivery | Pending |  |  |  |  | Pending
60 | 2026-09-30 | Sign-off date is the project end date by default | Sign-off | Pending |  |  |  |  | Pending
61 | 2026-09-30 | Changing the end date requires a reason and an evidence attachment | Sign-off | Pending |  |  |  |  | Pending
62 | 2026-09-30 | After that change, the sign-off date moves to the new end date | Sign-off | Pending |  |  |  |  | Pending
63 | 2026-09-30 | History of each change: who, when, old and new dates, reason | Sign-off | Pending |  |  |  |  | Pending
64 | 2026-09-30 | Project table shows only the main columns | Projects | Pending |  |  | ?? Confirm: which columns? |  | Pending
65 | 2026-09-30 | Show other columns or rows only when filters are applied | Projects | Pending |  |  | ?? Confirm: extra columns on filter, or rows load only after a filter? |  | Pending
66 | 2026-09-30 | Hovering a Late mark shows the reason and evidence | Attendance | Pending |  |  |  |  | Pending
67 | 2026-09-30 | Hovering 'Forgot to clock out' shows the reason and evidence | Attendance | Pending |  |  |  |  | Pending